## Data
Enter Activity/Event/Milestone | Enter Description | Critical Activity? | Start Day | End Day | Milestone Date | Filter 1a | Filter 1b | Filter 1c | Filter 1d | Filter 1e | Filter 1f | Filter 1g | Filter 1h | Filter 1i | Filter 1j | Filter 2a | Filter 2c | Filter 2e | Filter 2g | Filter 2i | Workstream 1 | Workstream 2 | Workstream 3 | External Link | Contact | Email
Grantmaking Policy Environmental Scan (including risk frameworks) | The MITRE team will review publicly available policy regarding grant processes to attain a firm understanding of how these policies protect against foreign interference in federal research. This could involve analysis of: relevant policies discovered through the MITRE Policynet tool; online articles or documentation publicly available; interviews conducted with MITRE SMEs or persons from grantmaking agencies; evaluation of existing risk frameworks used by major grantmaking agencies. | yes | 2021-03-29 | 2021-04-30 |  | Indirect | [14 empty] | Policy Assessment | Risk Management Framework Analysis | Data Sharing Model
Develop Policy Framework | Based on prior research, MITRE will create a policy framework or standard with which to compare existing grantmaking agency policy. | yes | 2021-04-12 | 2021-04-30 |  | Indirect | [9 empty] | Josef |  |  |  |  | Policy Assessment
Conduct Gap Analysis | MITRE will compare existing grantmaking policy to the Policy Framework to identify gaps and create actionable recommendations to address these gaps. | yes | 2021-05-03 | 2021-07-02 |  | Indirect | [14 empty] | Policy Assessment
Policy Assessment Results Complete | MITRE will develop a technical report of assessment results for public release. | yes |  |  | 2021-07-02 | Indirect | [14 empty] | Policy Assessment
Environmental Scan for Foreign Influence Mitigation Practices | The MITRE team will review publicly available risk criteria and mitigation practices with a focus on those meant to deter foreign influence. This could involve analysis of: publicly available documentation; risk frameworks from any government agency; interviews of MITRE or Sponsor SMEs. | yes | 2021-04-19 | 2021-05-21 |  | Indirect | [14 empty] | Risk Management Framework Analysis | Data Sharing Model
Create Modified Grantmaking Risk Management Framework | Based on scan information reviewing existing risk management practices at grantmaking agencies and leading practices for mitigating foreign influence, MITRE will create a modified risk management framework specifically focused on enhancing foreign influence mitigation practices. | yes | 2021-05-24 | 2021-07-02 |  | Indirect | [9 empty] | Evan |  |  |  |  | Risk Management Framework Analysis
Risk Management Framework Complete |  | yes |  |  | 2021-07-02 | Indirect | [14 empty] | Risk Management Framework Analysis
Identify MITRE opportunities to enhance existing grantmaking policies or risk management practices within sponsor environments. | Using identified opportunities from environmental scanning activities, engage key sponsors to identify opportunities to modify policy and risk management practices. | yes | 2021-05-17 | 2021-08-27 |  | Indirect | [14 empty] | Risk Management Framework Analysis | Policy Assessment
Attain grantmaking agency data | MITRE will define individual stakeholder requirements and protocols for sharing proprietary risk data and make a formal request for data to NIH, NSF, and other partner agencies regarding data needs. | yes | 2021-03-01 | 2021-03-26 |  | Indirect | [14 empty] | Data Sharing Model
Data received from NIH/NSF | This is a target date. Earlier would be better. | yes |  |  | 2021-03-26 | Indirect | [14 empty] | Data Sharing Model
Map out grantmaking process | MITRE will create or adapt an existing high level process that explains the general grantmaking process. | yes | 2021-03-29 | 2021-04-16 |  | Indirect | [14 empty] | Data Sharing Model
Identify data sharing opportunities | MITRE will map stakeholder-originated data sharing opportunities and requirements to grants management lifecycle stages. | yes | 2021-04-19 | 2021-04-30 |  | Indirect | [14 empty] | Data Sharing Model
Create data sharing model | MITRE will define the capabilities, functions, standards, roles and responsibilities, and best practice elements required to implement a F3RE risk data sharing model. | yes | 2021-05-03 | 2021-07-02 |  | Indirect | [14 empty] | Data Sharing Model
Data sharing model complete |  | yes |  |  | 2021-07-02 | Indirect | [14 empty] | Data Sharing Model
Integrate risk framework in sponsor environment | MITRE will coordinate with partner agency to integrate first 6 months of work into existing partner agency processes and workflows. | no | 2021-08-01 | 2021-12-31 |  | Direct | [14 empty] | Risk Management Framework Analysis
Measure maturity of risk framework in sponsor environment | MITRE will instantiate and monitor performance of the tailored framework, data, processes, and tools. | no | 2021-08-01 | 2021-12-31 |  | Direct | [14 empty] | Risk Management Framework Analysis
Establish a research integrity ISAC | MITRE will: - Investigate public/private information sharing models, such as the ISAC model, MITRE ATT&CK®, and others. - Map and evaluate applicable data sharing models against data sharing framework consolidated requirements and success criteria. - create an action plan to implement the F3RE stakeholder risk data-sharing model. - work with F3RE stakeholders to implement a data sharing system based on the model and framework. | no | 2021-08-01 | 2022-12-31 |  | Direct | [9 empty] | Jon |  |  |  |  | Data Sharing Model
Analyze data | MITRE will analyze partner organizations, capabilities, and data to: - Identify sponsor-specific compliance functions not currently integrated into evaluation of risk. - Identify the types and sources of information needed to provide awareness of current and future foreign government fundamental research areas of interest. - Develop use cases for a process, dataset, and tool to provide awareness of previously undetected areas of interest. | yes | 2021-03-29 | 2021-04-30 |  | Indirect | [14 empty] | Anticipatory Modeling
Develop model prototype and supporting process | MITRE will tailor a baseline process to integrate partner compliance functions into information gathering and analysis activities to inform analysis of foreign government fundamental research areas of interest. MITRE will collaborate with one or more partners to develop a prototype dataset and analysis tool to identify emerging fundamental research areas of concern and flag them for additional due diligence. | yes | 2021-05-03 | 2021-06-04 |  | Indirect | [14 empty] | Anticipatory Modeling
Test model | MITRE will collaborate with one or more partners to test the baseline process, prototype dataset, and analysis tool to flag fundamental research areas of concern for the stakeholder using current and historical data. | yes | 2021-06-07 | 2021-07-02 |  | Indirect | [14 empty] | Anticipatory Modeling
Refine model | MITRE will work with additional F3RE sponsors to: - Define a governance structure for the dataset and tool. - Expand implementation of the new process, dataset, and analysis tool across the federal grantmaking community. | yes | 2021-08-01 | 2021-12-31 |  | Direct | [14 empty] | Anticipatory Modeling
Publish lessons learned | MITRE will create a draft technical report on lessons learned from testing the model. | yes |  |  | 2021-07-02 | Indirect | [14 empty] | Anticipatory Modeling
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mark critical activities if you wish.
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To create objects with a range, enter start and end dates. If your row is a milestone, leave these fields blank. Either the start and end date fields should have data, or you milestone field should have data. Not both.
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Enter your milestone dates here. If your row has a start and end day, leave this blank. Either the start and end date fields should have data, or you milestone field should have data. Not both.
Note on G1: Kauzlarich, Josef A: This says Org but it could be an individual role.
Note on L1: Kauzlarich, Josef A: This says Org but it could be an individual role.
Note on Q1: Kauzlarich, Josef A: This says Org but it could be an individual role.
Note on Y1: Kauzlarich, Josef A: This is a link to more information relating to the activity housed outside the calendar.

## Filter Validation Lists
Funding Source | Staff | Workstream
Indirect | Josef | Policy Assessment
Direct | Evan | Risk Management Framework Analysis
| Jon | Data Sharing Model
Anticipatory Modeling

## Title
GPC RI Project Plan